2-Week Sprint Plan: EA v1.0 & Gap Remediation

April 6–17, 2026   |   3–4 people   |   17 gaps addressed   |   Target: v1 draft complete Apr 17   |   Hard deadline: Apr 30

| Gap / Task | ← Week 1: Apr 6–10 → | ← Week 2: Apr 13–17 → |
| --- | --- | --- |
|  | Apr 6 | Apr 7 | Apr 8 | Apr 9 | Apr 10 | 11 | 12 | Apr 13 | Apr 14 | Apr 15 | Apr 16 | Apr 17 | 18 | 19 |
| Owner colour key → | Person A: CoE Lead / Han Person B: Platform Architect Person C: Platform Engineer Person D: Domain Lead(s) |
| PRIORITY 1 — CRITICAL ¦ Must be complete by Apr 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Invisible ROI & impact tracking P1 — Critical Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Illusion of automation (coverage map) P1 — Critical Person D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Unknown quality standards (pipeline) P1 — Critical Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Tight coupling & brittle integrations P1 — Critical Person B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Siloed solutions — catalog platform P1 — Critical Person C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Lack of reusability — composability P1 — Critical Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| +A No integration middleware (EDA/ADR) P1 — Critical Person B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| +B No EE standardization P1 — Critical Person C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▲ P1 completion target: Friday, April 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 2 — IMPORTANT ¦ Must be complete by Apr 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Upgrade & lifecycle friction (EE images) P2 — Important Person C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Inconsistent logging (log transport arch) P2 — Important Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 Ambiguous patterns (scaffolding tool) P2 — Important Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Poor lifecycle tracking (consumed_by) P2 — Important Person C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 Skill gaps (baseline assessment) P2 — Important Person D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| +C Cross-team dependencies (dep graph) P2 — Important Person C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY 3 — FOUNDATIONAL ¦ Complete by Apr 24 (buffer before Apr 30 deadline) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 Platform friction (getting-started guide) P3 — Foundational Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 Cognitive overload (standards portal) P3 — Foundational Person A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| +D No maturity model (domain assessment) P3 — Foundational Person D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ★ v1 EA draft complete: Friday, April 17 ¦ Hard deadline: April 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Individual workstream assignments

Each person owns a distinct workstream. The work is designed to be parallel — no person should be blocked waiting for another during Week 1. Dependency points are noted in the RACI below.

| Person | Week 1 tasks (Apr 6–10) | Week 2 tasks (Apr 13–17) | Key deliverables | Gaps addressed |
| --- | --- | --- | --- | --- |
| Person A CoE Lead / Han | - Add business value fields to observability template (hours_saved, actions_completed, hosts_changed) - Enforce all 7 quality gates in CI pipeline - Define catalog-entry.yml schema and interface spec - Draft 3 new standards: Integration Arch, EE Standard, Discoverability | - Document log transport architecture per EE type - Build scaffolding tool (aap-new CLI skeleton) - Write getting-started guide for standards portal - Finalize EA v1.0 — incorporate all review comments | - Updated observability template with ROI fields - Pipeline gates enforced (CI config) - catalog-entry.yml schema published - Three new standards drafted - EA v1.0 final document | 1.1 1.3 2.3 2.4 3.2 4.2 4.3 |
| Person B Platform Architect | - Architecture decision record (ADR): select event bus / API gateway for integration layer - Document EDA rulebook standard and approved integration patterns - Define which workloads are AAP-appropriate vs. alternative runners - Diagram updated network architecture (integration layer + EDA paths) | - Review EA document sections 2–3 (architecture diagrams) - Validate integration layer security controls - Write AAP upgrade test pipeline plan - Support EA v1.0 final review | - ADR: integration layer technology selection - EDA rulebook standard document - Updated network/firewall diagram - Platform abstraction principle doc - AAP upgrade test pipeline plan | 2.1 2.2 +A |
| Person C Platform Engineer | - Stand up catalog platform (select tooling, create schema, seed 5+ entries) - Publish first versioned EE images to Automation Hub (base-rhel9, base-windows) - Add catalog registration gate to production pipeline - Block Default EE in pipeline — enforce EE declaration | - Implement consumed_by dependency tracking in catalog pipeline - Publish remaining EE images (network-ios, etc.) - Add EE and composability gates to pipeline - Build consolidated standards portal (single URL) | - Catalog platform live with 5+ seed entries - EE images published to Automation Hub - Pipeline gates: catalog + EE + composability - consumed_by tracking operational - Standards portal live | 3.1 3.3 +B +C |
| Person D Domain Lead(s) | - Automation coverage assessment: map ALL domain procedures to automated / partial / manual - Produce toil register for each domain - Identify highest-value unautomated procedures - Confirm manual baselines for top 5 procedures | - Skills baseline assessment: survey per engineer against 5 skill areas - Participate in initial domain maturity assessment (CoE-facilitated) - Review EA document domain-specific sections - Provide sign-off on coverage gap report | - Toil register (all domains) - Coverage gap report - Skills baseline results per domain - Domain maturity scores (initial) - EA domain section sign-off | 1.2 4.1 +D |

RACI matrix

R = Responsible (does the work)   A = Accountable (owns the outcome)   C = Consulted (input required)   — = No involvement

| Activity / Deliverable | Person A CoE Lead | Person B Platform Arch | Person C Platform Eng | Person D Domain Lead |
| --- | --- | --- | --- | --- |
| Automation coverage assessment & toil register | A | — | — | R |
| Business value fields — observability template | R | — | — | — |
| CI pipeline quality gates (all 10 standards) | A | — | R | — |
| Catalog platform — tooling, schema, seed entries | A | — | R | — |
| Integration layer ADR (technology selection) | C | R | — | — |
| EDA rulebook standard & integration patterns | A | R | — | — |
| EE image publication to Automation Hub | A | C | R | — |
| Three new standards (5.8, 5.9, 5.10) | R | C | — | — |
| catalog-entry.yml schema & composability spec | R | — | C | — |
| Pipeline: catalog + EE + composability gates | A | — | R | — |
| consumed_by dependency tracking in pipeline | A | — | R | — |
| Log transport architecture documentation | R | C | — | — |
| Scaffolding tool (aap-new CLI) | R | — | C | — |
| Skills baseline assessment | A | — | — | R |
| Domain maturity initial assessment | R | — | — | C |
| Getting-started guide & standards portal | R | — | C | — |
| EA document v1.0 final | R | C | C | C |

Meeting cadence

| Meeting | When | Who | Duration | Purpose |
| --- | --- | --- | --- | --- |
| Daily standup | 9:00 AM Mon–Fri | A, B, C, D | 15 min | Blockers only — what is stuck, what do you need from another person. Not a status report. |
| Week 1 kick-off | Apr 6, 9:30 AM | A, B, C, D | 45 min | Assign tasks, confirm owners, review Gantt, agree on done definitions. |
| Mid-sprint check | Apr 10, 2:00 PM | A, B, C, D | 30 min | P1 gate review — confirm all 8 P1 gaps have concrete outputs before week 2 starts. |
| Week 2 kick-off | Apr 13, 9:30 AM | A, B, C, D | 30 min | Week 2 task handoff, confirm P2 owners, surface any P1 carry-over. |
| EA v1 final review | Apr 16, 2:00 PM | A, B, C, D | 60 min | Walk through EA v1.0 draft together. All sections reviewed. Comments resolved before Apr 17. |
| Stakeholder share-out | Apr 17 | A + leadership | 30 min | Present v1 draft to engineering leadership. Confirm acceptance. |

Definition of done — per deliverable

A task is not done when the work is finished — it is done when the output is usable by another person without explanation. Use these definitions to self-check before marking a task complete in standup.

| Item | Done means… |
| --- | --- |
| Catalog platform | URL is live, schema is published, 5+ real automation assets have catalog entries, pipeline registration gate blocks promotion without a valid entry. |
| EE images | At least base-rhel9 and base-windows images are published to Automation Hub, pipeline rejects Default EE, one existing job template is migrated as proof. |
| Business value fields | hours_saved, actions_completed, and hosts_changed appear as structured fields in at least one real job's output and are visible in the observability platform. |
| Coverage assessment | A spreadsheet exists listing every operational procedure per domain, with status: automated / partial / manual, estimated hours per occurrence, and frequency per month. |
| New standards (5.8–5.10) | Each standard has: purpose, standard statement, author obligations, at least one compliant and one non-compliant code example, and a review checklist. Reviewed by Person B. |
| Pipeline quality gates | All 10 checklist gates run automatically on every PR to the main branch. A PR with a missing catalog-entry.yml or Default EE fails visibly, not silently. |
| EA document v1.0 | All [specify] and [TBD] placeholders in sections 1–9 are resolved. All three new standards are in the document. Reviewed and signed off by all four people. |
| Skills assessment | Every engineer in at least 3 domains has completed the self-assessment form. Results are summarised per domain and per skill area. |
| Standards portal | A single URL is accessible to all teams. It links to all 10 standards, the getting-started guide, the checklist, and the catalog browser. |

Risks and mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Catalog platform tooling takes longer than 2 days to stand up | Medium | Person C starts with the simplest viable option (a structured YAML file in Azure DevOps + a catalog API script) rather than waiting for a full tool decision. Can be migrated to a proper platform later. |
| ADR for integration layer cannot reach consensus in Week 1 | Medium | Person B documents the two leading options with trade-offs. The EA document can ship with the ADR in a 'decision pending' state — the standard exists regardless of which technology is chosen. |
| Domain leads unavailable for coverage assessment in Week 1 | High | Person A owns a lightweight template that domain leads can fill in async in 1–2 hours. Escalate to engineering managers if a domain lead has not started by Apr 8. This is the single highest-risk item in the sprint. |
| EA v1.0 review finds major gaps requiring significant rework | Low | Schedule the Apr 16 review as a structured walk-through with a pre-distributed comment template, not a free-form discussion. Limit scope of changes to content gaps — formatting and structure are frozen at Apr 14. |
| Person C blocked on Automation Hub access / licensing | Medium | Raise the Hub access request on Apr 6 Day 1. If access is not available by Apr 8, Person C shifts to catalog platform and pipeline gates — EE image work can follow in the week of Apr 20 without missing the Apr 30 deadline. |

Quick reference — gap to EA section mapping

| Gap | Description | EA section changed | Owner | Priority |
| --- | --- | --- | --- | --- |
| 1.1 | Invisible ROI tracking | §5.7, §8.4 | A | P1 — Critical |
| 1.2 | Illusion of automation | §9.4 (coverage map) | D | P1 — Critical |
| 1.3 | Unknown quality standards | §5, §10 (pipeline gates) | A | P1 — Critical |
| 2.1 | Tight coupling | §5.8, §2.2, §3.3 | B | P1 — Critical |
| 2.2 | Upgrade & lifecycle friction | §5.9, §4.1 | B + C | P2 — Important |
| 2.3 | Inconsistent logging | §5.7, §8.1 | A | P2 — Important |
| 2.4 | Ambiguous design patterns | Reference implementations, scaffolding | A | P2 — Important |
| 3.1 | Siloed solutions | §8.4, §5.10 | C | P1 — Critical |
| 3.2 | Lack of reusability | §5.10, §10.10 | A | P1 — Critical |
| 3.3 | Poor lifecycle tracking | §8.4, §5.10 §4 | C | P2 — Important |
| 4.1 | Skill gaps | §11.3 | D | P2 — Important |
| 4.2 | Platform friction | §11.4 | A | P3 — Foundational |
| 4.3 | Cognitive overload | §11.4 (standards portal) | A | P3 — Foundational |
| +A | No integration middleware | §5.8, §2.2, §3.3 | B | P1 — Critical |
| +B | No EE standardization | §5.9, §3.2, §4.1 | C | P1 — Critical |
| +C | Cross-team dependencies | §5.10 §4 | C | P2 — Important |
| +D | No maturity model | §9.5 | D | P3 — Foundational |