## Slide 1
SENIOR LEADERSHIP BRIEFING
Global Automation
Standards, Enablement & Roadmap
Automation Center of Excellence | Q2 2025
Automation Standards
Enablement Plan
Reporting → Enforcement
Notes: Today's update covers three outcomes: (1) automation standards as global guardrails, (2) the enablement plan to accelerate adoption across regions, and (3) a phased timeline moving from consistent reporting to sustainable enforcement. Goal: inform SLT on progress, align on what 'good' looks like globally, and confirm the near-term plan to scale safely without slowing delivery.

## Slide 2
Purpose & Discussion Agenda
01
ALIGNMENT ASK
Standards Direction
Confirm alignment on outcome-focused guardrails that enable regional flexibility within a consistent global framework.
02
ALIGNMENT ASK
Enablement Plan
Validate the enablement approach and identify where leadership can help remove barriers to adoption across regions.
03
ALIGNMENT ASK
Reporting → Enforcement Roadmap
Align on the phased timeline—when measurement begins, when it becomes operational gating, and what fair enforcement looks like.
Closing segment: KPIs & leadership value — what success looks like, how this reduces risk, and what's in it for the enterprise.
Notes: This is a high-level readout designed for alignment and discussion, not a deep technical review. Three prompts: (1) Confirm standards direction—guardrails, not rigid prescriptions. (2) Confirm enablement plan and where leadership can help remove barriers. (3) Align on the reporting-to-enforcement roadmap. Will close with KPIs and what's in it for leadership.

## Slide 3
Where We Are Today
Standards
FROM: Distributed, inconsistent
▶
TO: Global guardrails defined—outcome-focused, platform-neutral, regionally flexible
55%
Enablement
FROM: Ad hoc guidance
▶
TO: Structured onboarding, starter kits & regional clinics in development
40%
Reporting
FROM: No shared scorecard
▶
TO: Scorecard dimensions defined; baseline data collection underway
30%
Enforcement
FROM: No gating
▶
TO: Phased introduction planned—enforcement follows stable reporting & enablement
15%
Notes: We've progressed from distributed automation activity toward a global model. Standards are defined as guardrails. Enablement is transitioning from ad hoc to repeatable onboarding and starter kits. Reporting is being defined as a scorecard giving SLT visibility into adoption, reliability, reuse, and risk. Next step: establish baseline reporting, then introduce enforcement with exception-and-learning process.

## Slide 4
Automation Standards: What 'Good' Looks Like
Guiding
Principle
"Consistency without
rigidity — regional
flexibility within
global guardrails."
Standards are outcome-based, not prescriptive. Teams implement differently based on maturity and constraints—the outcomes remain consistent.
Reliability
Automated testing requirements
Monitoring readiness at deploy
Failure detection & alerting
Governance
Auditability & traceability
Approval gates where risk warrants
Exception documentation & learning
Scalability
Reusable reference patterns
Documentation standards
Platform alignment & portability
Notes: Standards define what 'good' looks like so automation is reliable, governable, and scalable. The key is consistency without rigidity—regions implement differently based on maturity, but outcomes remain consistent. Standards reduce operational surprises, increase reuse, and create an enterprise-quality baseline that teams can apply in real pipelines without slowing delivery.

## Slide 5
Standards in Practice: Federated Operating Model
Global COE
Guardrails
Americas
EMEA
Asia (ex-JP)
Japan
Lightweight Reviews
Touchpoints at design & release gates only where risk warrants it
Documented Exceptions
Deviations expected and captured as learning—not treated as failures
Continuous Evolution
Standards updated via CoP feedback and regional insights
Notes: The operating approach is federated: global guardrails with regional execution. Standards apply through lightweight review touchpoints, not centralized approvals for every change. Deviations are expected; what matters is a documented exception process that captures learning. This prevents shadow automation while preserving delivery speed. Standards evolve through champion and practitioner feedback.

## Slide 6
Automation Enablement Plan: Accelerating Adoption
1
Structured Onboarding
Starter guide + first automation journey
Role-based training tracks
Baseline standards walkthrough
2
Starter Kits & Patterns
Reference implementation templates
Approved pipeline patterns
Sample configs for key platforms
3
Workshops & Clinics
Builder / reviewer / operator tracks
Office hours (global + regional)
COE + Champions co-delivery
4
Two-Way Feedback Loop
Regions contribute patterns back
Champion insights shape standards
Library grows with adoption
SUCCESS MEASURE: Time to first successful automation · Reuse of approved patterns · Reliability improvement over 90 days
Notes: Enablement turns guardrails into adoption at scale. The plan centers on structured onboarding, starter kits, role-based workshops, and office hours co-run by the global COE and regional champions. Success measure is not training completion—it's time-to-first-successful-automation, reuse of approved patterns, and measurable reliability improvement. Enablement is also a two-way channel: regions contribute back patterns and lessons.

## Slide 7
Global Model: COE · Community of Practice · Champions
Global COE
OWNS WHAT GOOD LOOKS LIKE
Accountable for global standards & governance
Drives enablement strategy & starter kits
Integration point for feedback & continuous improvement
NOT a delivery bottleneck—a working body for outcomes
Community of Practice
SHARES HOW IT WORKS
Knowledge sharing & peer learning forum
Translates standards into practical understanding
Incubates emerging practices & tools
Cross-region connection: US, EMEA, APAC
Regional Champions
DRIVES LOCAL EXECUTION
Local face of global strategy—enablement, not policing
Hands-on support for applying standards in context
Surface regional friction back to COE
Run local sessions; lead CoP discussions
HOW TO LEVERAGE CHAMPIONS: Define clear expectations · Allocate protected time · Recognize as a formal role · Measure by adoption outcomes—not compliance counts
Notes: COE is accountable for the global operating model. The Community of Practice is the practitioner engine—shares what works, surfaces challenges, accelerates learning. Champions are the multipliers, the local face of strategy. To leverage champions: define clear expectations (enablement, not policing), allocate protected time, recognize them as a formal role. Success = adoption and improved outcomes, not enforcement gatekeeping.

## Slide 8
Reporting Framework: What SLT Will See
Adoption
Teams onboarded & active
Pipeline coverage %
Standards utilization rate
Reliability
Automation success rate
Failure recurrence reduction
Incident linkage trend
Reuse
Approved pattern usage
Reduction in duplicated effort
Contributions to global library
Governance
Exception volume & resolution time
Audit readiness signals
High-risk automation hotspots
Reporting is not for its own sake. SLT uses this scorecard to steer priorities: where to invest enablement, where to remove barriers, and where risk requires tighter controls. Reporting is the prerequisite to enforcement—it makes expectations measurable and enables targeted intervention instead of broad mandates.
Notes: Reporting is the bridge between intention and accountability. The scorecard rolls up adoption, reliability, reuse, and governance (risk). SLT uses it to steer: where to invest, where to remove barriers, where risk needs tighter controls. Scorecard also supports regional transparency—showing progress without forcing identical implementation. Reporting is the prerequisite to enforcement.

## Slide 9
Roadmap: Reporting → Standards Enforcement
Q2 2025
Phase 1
Foundation
Finalize global standards (STD-01→07)
Launch reporting scorecard
Identify regional champions
Launch Community of Practice forum
Q3 2025
Phase 2
Enablement
Deploy starter kits & workshops
Introduce standards reviews at gates
Formal exception process live
Champion-led regional sessions begin
Q4 2025
Phase 3
Enforcement
Expand regional adoption coverage
Mature & tune scorecard baselines
Enforcement gates for high-risk automation
Scale reuse pattern library globally
Enforcement gates become active only after reporting is stable and enablement is broadly available — ensuring gating is fair, predictable, and targeted to risk.
Notes: Phase 1: Establish baseline standards, reporting scorecard, champion network, and CoP forum. Phase 2: Enablement kits and workshops, standards reviews at gates, formal exception process. Phase 3: Expand regional adoption, mature scorecard, introduce enforcement gates for high-risk automation. Enforcement becomes real only when reporting is stable and enablement is broadly available—making gates fair and predictable.

## Slide 10
KPIs & What's In It for Leadership
Leadership
Value
⬇ Fewer incidents from automation failures
📈 More predictable delivery across regions
♻ Scalable reuse — less duplicated effort
🔍 Full visibility via consistent scorecard
✅ Audit readiness & governance confidence
Proposed KPI Framework
Adoption
Teams onboarded; active pipeline count using standards
Reliability
Automation success rate; failure recurrence reduction; incident trend
Reuse
Approved pattern usage %; reduction in duplicated automation effort
Governance
Exception volume & avg. time-to-resolution; audit readiness signals
Value
Hours saved or cycle time reduced (where credibly measurable)
Goal: Directional visibility to steer investment, reduce risk, and demonstrate quarter-over-quarter progress — not perfect accounting.
Notes: For leadership, the benefit is control with speed: fewer incidents from automation failures, more predictable delivery, scalable reuse. KPIs: Adoption (teams onboarded, active pipelines using standards), Reliability (success rate, failure recurrence, incident trend), Reuse (pattern usage, duplication reduction), Governance (exceptions volume, audit readiness), Value (hours saved where credibly measured). Goal is directional visibility—not perfect accounting.

## Slide 11
Alignment & Next Steps
1
Standards as Guardrails
Outcome-based global standards with regional flexibility—the foundation for enterprise-quality automation.
2
Enablement as Engine
Starter kits, workshops, and champion support drive adoption. Regions contribute back to strengthen the global library.
3
Phased Reporting → Enforcement
Baseline reporting first. Enforcement gates only when measurement is stable and enablement is broadly available.
WHERE SLT CAN HELP
◆ Remove adoption barriers in-region ◆ Support champion capacity & time allocation ◆ Reinforce this as an enterprise capability—not a regional project
Next update: scorecard-driven, showing adoption progress, risk reduction, and readiness for enforcement gates.
Notes: Closing: aligning on three things—standards as outcome-based guardrails, enablement as the adoption engine, and a phased roadmap that is fair and scalable. Near-term focus: baseline reporting and enabling regions with starter kits, workshops, and champion support. SLT can help by removing adoption barriers, supporting champion capacity, and reinforcing that this is an enterprise capability. Next updates will be scorecard-driven.